### Appendix C

### Budget

(For Reference Only – Do Not Submit)

Sample Grant Period: July 1, 2026 – April 30, 2027
Project Duration: 10 months
Total Students Served: 120

## I. Personnel Costs

Project Coordinator

- Role: Outreach, recruitment, coordination, reporting

- Rate: $35/hour

- Time: 30 hours/month × 10 months

- Total Cost: $10,500

STEM Curriculum Specialist

- Role: Develop and finalize 24-week STEM curriculum

- Rate: $50/hour

- Time: 120 total hours

- Total Cost: $6,000

STEM Instructors (3)

- Role: Deliver weekly after-school STEM instruction

- Rate: $45/hour

- Time: 2 hours/week × 24 weeks × 3 instructors

- Total Cost: $6,480

Evaluation Consultant

- Role: Pre/post assessments, analysis, reporting

- Rate: $60/hour

- Time: 90 total hours

- Total Cost: $5,400

Program Assistant

- Role: Attendance tracking, logistics, data entry

- Rate: $25/hour

- Time: 20 hours/month × 10 months

- Total Cost: $5,000

Subtotal – Personnel: $33,380

## II. Fringe Benefits (20%)

- Fringe benefits calculated at 20% of total personnel costs

- Covers payroll taxes, insurance, and employee benefits

Total – Fringe Benefits: $6,676

## III. Program Supplies & Materials

STEM Kits & Equipment

- Description: Robotics kits, coding equipment, engineering tools

- Cost: $18,000

Consumable Materials

- Description: Science supplies and replacement parts

- Cost: $9,000

Curriculum & Instructional Materials

- Description: Printing, instructional guides, curriculum licenses

- Cost: $3,000

Student Supplies

- Description: Notebooks, safety gear, take-home learning materials

- Cost: $6,000

Subtotal – Supplies & Materials: $36,000

## IV. Evaluation Costs

Assessment Tools & Instruments

- Description: Surveys and pre/post assessments

- Cost: $3,000

Data Management & Reporting Tools

- Description: Data storage systems and analysis software

- Cost: $3,500

Subtotal – Evaluation: $6,500

## V. Outreach & Recruitment

Outreach Materials

- Description: Printing, translation services, and digital outreach

- Cost: $3,000

Community Engagement Activities

- Description: Information sessions and partner coordination

- Cost: $2,000

Subtotal – Outreach: $5,000

## VI. Facilities & Operations

Space Rental

- Description: After-school instructional sites

- Cost: $6,000

Utilities, Insurance & Custodial Costs

- Description: Program-related portion of facility costs

- Cost: $3,000

Transportation Support

- Description: Student transportation assistance

- Cost: $2,500

Subtotal – Facilities & Operations: $11,500

## VII. Administrative / Indirect Costs (Approx. 10%)

- Includes fiscal management, compliance, reporting, and administrative oversight

- Reduced to balance total project cost to $100,000

Subtotal – Administrative / Indirect Costs: $937

## TOTAL PROJECT BUDGET SUMMARY

- Personnel: $33,380

- Fringe Benefits: $6,676

- Supplies & Materials: $36,000

- Evaluation: $6,500

- Outreach & Recruitment: $5,000

- Facilities & Operations: $11,500

- Administrative / Indirect: $937

TOTAL PROJECT COST: $100,000